## How to use
RACI Chart (Responsibility Assignment Matrix)
Free template from The Project Sheet · theprojectsheet.com
Want more? Pro version: Project Management Pro Bundle
A RACI chart that shows who is Responsible, Accountable, Consulted and Informed for every task, and checks the matrix for you.
How to use this template
1 | On the RACI sheet, rename the six role columns to the people or roles on your project.
2 | List your tasks or deliverables in column B (up to 20).
3 | Pick R, A, C or I from the dropdown in each cell. Leave a cell empty if that role has no part in the task.
4 | The Check column confirms each task has exactly one A and at least one R.
5 | Use the workload table to spot people who are Responsible for too much or Consulted on everything.
Good to know
• Only one person should be Accountable for each task, so decisions never fall between two people.
• Share the RACI chart at kick-off and revisit it when the team or scope changes.
• Yellow cells are inputs. Every other figure is a formula, so do not type over it.
• The sample figures are only there to show how the template works. Replace them with your own.
• Works in Google Sheets too: File > Import > Upload, then open in Google Sheets.
• Tutorial and more free templates: https://theprojectsheet.com

## RACI
RACI Chart (Responsibility Assignment Matrix)
Free template from The Project Sheet · theprojectsheet.com
Want more? Pro version: Project Management Pro Bundle
R = Responsible (does the work) · A = Accountable (owns the result, only one) · C = Consulted · I = Informed
# | Task or deliverable | Project sponsor | Project manager | Lead developer | Designer | QA lead | Marketing lead | Check
1 | Approve project charter | A | R | C | I | I | C | OK
2 | Define requirements | C | A | R | C | C | C | OK
3 | Create project plan | A | R | C | C | C | I | OK
4 | Design user interface | I | A | C | R | C | C | OK
5 | Build features | I | A | R | C | I | I | OK
6 | Test release | I | A | C | I | R | I | OK
7 | Prepare launch campaign | C | I | I | C | I | A | Needs at least one R
8 | Go / no-go decision | A | R | C | I | C | C | OK
9 | Launch to customers | I | A | R | I | C | R | OK
10 | Post-launch review | C | A | R | C | C | C | OK
Workload by role
| Responsible (R) | 0 | 3 | 4 | 1 | 1 | 1
| Accountable (A) | 3 | 6 | 0 | 0 | 0 | 1
| Consulted (C) | 3 | 0 | 5 | 5 | 6 | 5
| Informed (I) | 4 | 1 | 1 | 4 | 3 | 3
| Rows with a problem | 1